## Gantt Chart
ParkEase – Work Contribution Timeline (Gantt Chart)
Project Start: | 2026-08-04 |  | Project End: | 2026-09-08
Team: | Yuvraj | Tanishk | Soham
No. | Task | Assigned To | Start | End | Duration (days) | Start Offset | Duration | Label
1 | Project conceptualization, planning & proposal (PPT) | Yuvraj | 2026-08-04 | 2026-08-08 | 5 | 0 | 5 | Yuvraj: Project conceptualization, planning & proposal (PPT)
2 | Contributed to proposal – objectives & scope | Tanishk | 2026-08-04 | 2026-08-08 | 5 | 0 | 5 | Tanishk: Contributed to proposal – objectives & scope
3 | Prepared project proposal in LaTeX | Soham | 2026-08-04 | 2026-08-08 | 5 | 0 | 5 | Soham: Prepared project proposal in LaTeX
4 | Backend setup – Node.js, MongoDB, Auth APIs | Yuvraj | 2026-08-11 | 2026-08-15 | 5 | 7 | 5 | Yuvraj: Backend setup – Node.js, MongoDB, Auth APIs
5 | Frontend development – UI, layout, navigation | Tanishk | 2026-08-11 | 2026-08-15 | 5 | 7 | 5 | Tanishk: Frontend development – UI, layout, navigation
6 | Backend development start – Node.js & MongoDB | Soham | 2026-08-11 | 2026-08-15 | 5 | 7 | 5 | Soham: Backend development start – Node.js & MongoDB
7 | Parking slot, reservation & payment backend | Yuvraj | 2026-08-18 | 2026-08-22 | 5 | 14 | 5 | Yuvraj: Parking slot, reservation & payment backend
8 | Data Flow Diagram (DFD) using Draw.io | Tanishk | 2026-08-18 | 2026-08-22 | 5 | 14 | 5 | Tanishk: Data Flow Diagram (DFD) using Draw.io
9 | Backend APIs – auth, slots, reservations, payments | Soham | 2026-08-18 | 2026-08-22 | 5 | 14 | 5 | Soham: Backend APIs – auth, slots, reservations, payments
10 | Admin functionalities & API testing (Postman) | Yuvraj | 2026-08-25 | 2026-08-29 | 5 | 21 | 5 | Yuvraj: Admin functionalities & API testing (Postman)
11 | ER Diagram & Swimlane Diagram (Draw.io) | Tanishk | 2026-08-25 | 2026-08-29 | 5 | 21 | 5 | Tanishk: ER Diagram & Swimlane Diagram (Draw.io)
12 | API testing (Postman) & Use Case Diagram update | Soham | 2026-08-25 | 2026-08-29 | 5 | 21 | 5 | Soham: API testing (Postman) & Use Case Diagram update
13 | Use Case Diagram & DFD creation | Yuvraj | 2026-09-01 | 2026-09-03 | 3 | 28 | 3 | Yuvraj: Use Case Diagram & DFD creation
14 | Frontend prototype refinement | Tanishk | 2026-09-01 | 2026-09-03 | 3 | 28 | 3 | Tanishk: Frontend prototype refinement
15 | DFD development | Soham | 2026-09-01 | 2026-09-03 | 3 | 28 | 3 | Soham: DFD development
16 | Backend integration into prototype; PPT update | Yuvraj | 2026-09-04 | 2026-09-06 | 3 | 31 | 3 | Yuvraj: Backend integration into prototype; PPT update
17 | Diagram visuals for documentation/PPT | Tanishk | 2026-09-04 | 2026-09-06 | 3 | 31 | 3 | Tanishk: Diagram visuals for documentation/PPT
18 | DFD & Use Case Diagram review/refinement | Soham | 2026-09-04 | 2026-09-06 | 3 | 31 | 3 | Soham: DFD & Use Case Diagram review/refinement
19 | Prototype deployed on Vercel; final verification | Yuvraj | 2026-09-07 | 2026-09-08 | 2 | 34 | 2 | Yuvraj: Prototype deployed on Vercel; final verification
20 | Final review of frontend, diagrams & docs | Tanishk | 2026-09-07 | 2026-09-08 | 2 | 34 | 2 | Tanishk: Final review of frontend, diagrams & docs
21 | Final verification of backend & diagrams | Soham | 2026-09-07 | 2026-09-08 | 2 | 34 | 2 | Soham: Final verification of backend & diagrams